## Test_Report
Test Summary Report
Project Name: | Idestination | Total No. of Test cases: |  |  |  | Total Completion Percentage |  | Defects |  |  |  |  | Grand Total
Project Owner: |  | Planned | Passed | Failed | Not Executed |  |  | Show Stopper | Critical | Major | Minor | UI/Cosmetic
Prepared By: | Ajinkya Patil | [5 empty] | Open | 0 | 0 | 0 | 0 | 0 | 0
Executed By: |  | 22 | 0 | 0 | 22 | 0% | Closed | 0 | 0 | 0 | 0 | 0
Execution Start Date: | [6 empty] | Total | 0 | 0 | 0 | 0 | 0

## Summary
Test Summary Data
Sr. No. | Sprint | Component/ Feature | Module/ Feature ID | No. Of Test Cases: |  |  |  | Completion % | Defects | [9 empty] | Total Bugs
|  |  |  | Planned | Passed | Failed | Not Executed |  | Show Stopper |  | Critical |  | Major |  | Minor |  | UI/Cosmetic
[9 empty] | Open | Closed | Open | Closed | Open | Closed | Open | Closed | Open | Closed
1 | Sprint 1 | orgniser_event | TC_ad01 | 14 | 0 | 0 | 14 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Sprint 2 | user_event | TC_ur01 | 8 | 0 | 0 | 8 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
0
0
0
0
0
0
0
0
0
0

## orgniser_poll
Project Name: |  | Idestination |  | Test Data
Sprint: |  | 1 |  | URL: http://idestination-dev.iksulabeta.com
Component/Feature: |  | My Opinion |  | Username:
Component/Feature ID: |  |  |  | Password:
Prepared By: |  | Ajinkya Patil
Approved By(BA/TL):
Functional Requirement | Test Case ID | Objective/Description | Pre-Requisite/ Test Data | Browsers/ Devices | Steps | Expected Result | Actual Result | Status | Comments | Bug Id
| TC_ad01 | To verify user able to login with invalid username and password | TEST url | Desktop | 1)Enter URL 2)Enter invalid user id and password | Error message should be disply
| TC_ad02 | To verify user able to login with valid username and password | TEST url | Desktop | 1)Enter URL 2)Enter valid user id and password | 1)User should be sucessfully login and redirected to home page
| TC_ad03 | check functionality of hover on "Iconnect" | TEST url | Desktop | 1)Enter URL 2)Enter valid user id and password 3)Move curser on "iconnect" option | 1)Color of "iconnect"should be red 2)dropdown option list open
| TC_ad04 | check functionality of"MyOpinion" | TEST url | Desktop | 1)Enter URL 2)Enter valid user id and password 3)Move curser on "iconnect" option 4)click on "MyOpinion" | 1)Existing question for poll shold be displayed 2)create poll/take poll options should be displayed
| TC_ad05 | check functionality of"Create poll"button | TEST url | Desktop | 1)Enter URL 2)Enter valid user id and password 3)Move curser on "iconnect" option 4)click on "MyOpinion" 5)click on "create poll"button | form should be display for create new poll
| TC_ad06 | check functionality of "save" button in Create event with empty feild | TEST url | Desktop | 1)Enter URL 2)Enter valid user id and password 3)Move curser on "iconnect" option 4)click on "MyOpinion" 5)click on "create new "poll"button 6)click on save button | error message should be displayed for required frilds
| TC_ad07 | check functionality of"priview" button with valid data | TEST url | Desktop | 1)Enter URL 2)Enter valid user id and password 3)Move curser on "iconnect" option 4)click on "My Opinion" 5)click on "create poll "button 6)enter valid data 7)click on "priview" button | priview should be displayed in proper manner
| TC_ad08 | check functionality of"save" button with valid data | TEST url | Desktop | 1)Enter URL 2)Enter valid user id and password 3)Move curser on "iconnect" option 4)click on "My Opinion" 5)click on "create poll "button 6)enter valid data 7)click on "save" button | poll should be save and disply with existing poll questions
| TC_ad09 | check edit functionality | TEST url | Desktop | 1)Enter URL 2)Enter valid user id and password 3)Move curser on "iconnect" option 4)click on "My Opinion" 5)click on question display for opinion poll | poll section open in new window sepratly
| TC_ad10 | check edit functionality | TEST url | Desktop | 1)Enter URL 2)Enter valid user id and password 3)Move curser on "iconnect" option 4)click on "My Opinion" 5)click on question display for opinion poll 6)click on "edit" option | poll should be unable for update
| TC_ad11 | check edit functionality with necessary changes | TEST url | Desktop | 1)Enter URL 2)Enter valid user id and password 3)Move curser on "iconnect" option 4)click on "My Opinion" 5)click on question display for opinion poll 6)click on "edit" option 7)make necessary changes 8)click on save button | information should be updated and displayed.conformation message should be displayed
| TC_ad12 | check Read more functionality | TEST url | Desktop | 1)Enter URL 2)Enter valid user id and password 3)Move curser on "iconnect" option 4)click on "My Opinion" 5)click on Read more | opinion quetions open in details
| TC_ad13 | check add new comment functionality | TEST url | Desktop | 1)Enter URL 2)Enter valid user id and password 3)Move curser on "iconnect" option 4)click on "My Opinion" 5)click on add new comment | feilds are unable for writing comment
| TC_ad14 | check add new comment functionality | TEST url | Desktop | 1)Enter URL 2)Enter valid user id and password 3)Move curser on "iconnect" option 4)click on "My Opinion" 5)click on add new comment 6)enter comment 7)click on save button | comment should be saved

## user_poll
Project Name: |  | Idestination |  | Test Data
Sprint: |  | 1 |  | URL: http://idestination-dev.iksulabeta.com
Component/Feature: |  | My Opinion |  | Username:
Component/Feature ID: |  |  |  | Password:
Prepared By: |  | Ajinkya Patil
Approved By(BA/TL):
Functional Requirement | Test Case ID | Objective/Description | Pre-Requisite/ Test Data | Browsers/ Devices | Steps | Expected Result | Actual Result | Status | Comments | Bug Id
| TC_ur01 | To verify user able to login with invalid username and password | TEST url | Desktop | 1)Enter URL 2)Enter invalid user id and password | Error message should be disply
| TC_ur02 | To verify user able to login with valid username and password | TEST url | Desktop | 1)Enter URL 2)Enter valid user id and password | 1)User should be sucessfully login and redirected to home page
| TC_ur03 | check functionality of hover on "Iconnect" | TEST url | Desktop | 1)Enter URL 2)Enter valid user id and password 3)Move curser on "iconnect" option | 1)Color of "iconnect"should be red 2)dropdown option list open
| TC_ur04 | check functionality of"MyOpinion" | TEST url | Desktop | 1)Enter URL 2)Enter valid user id and password 3)Move curser on "iconnect" option 4)click on "MyOpinion" | 1)Existing question for poll shold be displayed 2)create poll/take poll options should be displayed
| TC_ur05 | Check functionality of "vote" function | TEST url | Desktop | 1)Enter URL 2)Enter valid user id and password 3)Move curser on "iconnect" option 4)click on "My Opinion" 5)select any option 6)click on "vote" button | vote should be save with selected option.
| TC_ur06 | check Read more functionality | TEST url | Desktop | 1)Enter URL 2)Enter valid user id and password 3)Move curser on "iconnect" option 4)click on "My Opinion" 5)click on Read more | opinion quetions open in details
| TC_ur07 | check add new comment functionality | TEST url | Desktop | 1)Enter URL 2)Enter valid user id and password 3)Move curser on "iconnect" option 4)click on "My Opinion" 5)click on add new comment | feilds are unable for writing comment
| TC_ur08 | check add new comment functionality | TEST url | Desktop | 1)Enter URL 2)Enter valid user id and password 3)Move curser on "iconnect" option 4)click on "My Opinion" 5)click on add new comment 6)enter comment 7)click on save button | comment should be saved

## Sheet5
image after save events
ui issue when selecting options
edit option for users
opinion option for event creator
Enter Friends Limit-function not working
data alignment-invited people and date
limit of invitation when closed event
behaviour in edit mode
once unlike than email not be send
if same person like event..mail should be not send
dropdown list on comment