## Test_Report
Test Summary Report
Project Name: | Idestination | Total No. of Test cases: |  |  |  | Total Completion Percentage |  | Defects |  |  |  |  | Grand Total
Project Owner: |  | Planned | Passed | Failed | Not Executed |  |  | Show Stopper | Critical | Major | Minor | UI/Cosmetic
Prepared By: | Ajinkya Patil | [5 empty] | Open | 0 | 0 | 1 | 0 | 0 | 5
Executed By: |  | 16 | 11 | 5 | 0 | 68.75% | Closed | 0 | 0 | 4 | 0 | 0
Execution Start Date: | [6 empty] | Total | 0 | 0 | 5 | 0 | 0

## Summary
Test Summary Data
Sr. No. | Sprint | Component/ Feature | Module/ Feature ID | No. Of Test Cases: |  |  |  | Completion % | Defects | [9 empty] | Total Bugs
|  |  |  | Planned | Passed | Failed | Not Executed |  | Show Stopper |  | Critical |  | Major |  | Minor |  | UI/Cosmetic
[9 empty] | Open | Closed | Open | Closed | Open | Closed | Open | Closed | Open | Closed
1 | Sprint 1 | orgniser_event | TC_OR01 | 11 | 7 | 4 | 0 | 63.64% | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 4
2 | Sprint 2 | user_event | TC_UR01 | 5 | 4 | 1 | 0 | 80% | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1
0
0
0
0
0
0
0
0
0
0
0

## orgniser_event
Project Name: |  | Idestination |  | Test Data
Sprint: |  | 1 |  | URL: http://idestination-dev.iksulabeta.com
Component/Feature: |  | Social events |  | Username:
Component/Feature ID: |  |  |  | Password:
Prepared By: |  | Ajinkya Patil
Approved By(BA/TL):
Functional Requirement | Test Case ID | Objective/Description | Pre-Requisite/ Test Data | Browsers/ Devices | Steps | Expected Result | Actual Result | Status | Comments | Bug Id
| TC_OR01 | To verify user able to login with invalid username and password | TEST url | Desktop | 1)Enter URL 2)Enter invalid user id and password | Error message should be disply | Error message is displying | pass
| TC_OR02 | To verify user able to login with valid username and password | TEST url | Desktop | 1)Enter URL 2)Enter valid user id and password | 1)User should be sucessfully login and redirected to home page | 1)User sucessfully login and redirecting to home page | pass
| TC_OR03 | check functionality of hover on "Iconnect" | TEST url | Desktop | 1)Enter URL 2)Enter valid user id and password 3)Move curser on "iconnect" option | 1)Color of "iconnect"should be red 2)dropdown option list open | 1)Color of "iconnect"is red 2)dropdown option list is open | pass
| TC_OR04 | check functionality of"Iconnect" | TEST url | Desktop | 1)Enter URL 2)Enter valid user id and password 3)Move curser on "iconnect" option 4)click on "isocial events" | 1)Color of "iconnect"should be red 2)dropdown option list open 3)user should be redirected to "isocial event"page 4)create new event button should be displayed | 1)Color of "iconnect"is red 2)dropdown option list is open 3)user is redirecting to "isocial event"page 4)create new event button is displaying | pass
| TC_OR05 | check functionality of"create new event" button | TEST url | Desktop | 1)Enter URL 2)Enter valid user id and password 3)Move curser on "iconnect" option 4)click on "isocial events" 5)click on "create new event"button | create social event page should be displayed | create social event page is displaying | pass
| TC_OR06 | check functionality of"save" button with empty feild | TEST url | Desktop | 1)Enter URL 2)Enter valid user id and password 3)Move curser on "iconnect" option 4)click on "isocial events" 5)click on "create new event"button 6)click on save button | error message should be display for mandetory feilds | error message is displaying for mandetory feilds | pass
| TC_OR07 | check functionality of"priview" button with valid data | TEST url | Desktop | 1)Enter URL 2)Enter valid user id and password 3)Move curser on "iconnect" option 4)click on "isocial events" 5)click on "create new event"button 6)enter valid data 7)click on "priview" button | Privew should be displayed | Privew is displaying | Pass
| TC_OR08 | check functionality of"save" button with valid data | TEST url | Desktop | 1)Enter URL 2)Enter valid user id and password 3)Move curser on "iconnect" option 4)click on "isocial events" 5)click on "create new event"button 6)enter valid data 7)click on save button | 1)Event should be save 2)mail should be send to taged usres. 3)created event should be displayed in orgnisers and usres account. | 1)Date showing wrong 2)image | FAIL | 1)Event not showing is current date selected
| TC_OR09 | check functionality of"save" button with valid data | TEST url | Desktop | 1)Enter URL 2)Enter valid user id and password 3)Move curser on "iconnect" option 4)click on "isocial events" 5)click on "create new event"button 6)enter valid data 7)click on save button | 1)Event should be save 2)mail should be send to taged usres. 3)created event should be displayed in orgnisers and usres account. | 1)Date showing wrong 2)image | FAIL | Create new event:-UI issue
| TC_OR10 | check functionality of"save" button with valid data | TEST url | Desktop | 1)Enter URL 2)Enter valid user id and password 3)Move curser on "iconnect" option 4)click on "isocial events" 5)click on "create new event"button 6)enter valid data 7)click on save button | 1)Event should be save 2)mail should be send to taged usres. 3)created event should be displayed in orgnisers and usres account. | 1)Date showing wrong 2)image | FAIL | ISocial event:-UI issue
| TC_OR11 | check functionality of"save" button with valid data | TEST url | Desktop | 1)Enter URL 2)Enter valid user id and password 3)Move curser on "iconnect" option 4)click on "isocial events" 5)click on "create new event"button 6)enter valid data 7)click on save button | 1)Event should be save 2)mail should be send to taged usres. 3)created event should be displayed in orgnisers and usres account. | 1)Date showing wrong 2)image | FAIL | Create new event:-"Invite Other Peoples" option enable

## user_event
Project Name: |  | Idestination |  | Test Data
Sprint: |  | 1 |  | URL: http://idestination-dev.iksulabeta.com
Component/Feature: |  | Social events |  | Username:
Component/Feature ID: |  |  |  | Password:
Prepared By: |  | Ajinkya Patil
Approved By(BA/TL):
Functional Requirement | Test Case ID | Objective/Description | Pre-Requisite/ Test Data | Browsers/ Devices | Steps | Expected Result | Actual Result | Status | Comments | Bug Id
| TC_UR01 | To verify user able to login with invalid username and password | TEST url | Desktop | 1)Enter URL 2)Enter invalid user id and password | Error message should be disply | Error message is displying | pass
| TC_UR02 | To verify user able to login with valid username and password | TEST url | Desktop | 1)Enter URL 2)Enter valid user id and password | 1)User should be sucessfully login and redirected to home page | 1)User sucessfully login and redirecting to home page | pass
| TC_UR03 | check functionality of hover on "Iconnect" | TEST url | Desktop | 1)Enter URL 2)Enter valid user id and password 3)Move curser on "iconnect" option | 1)Color of "iconnect"should be red 2)dropdown option list open | 1)Color of "iconnect"is red 2)dropdown option list is open | pass
| TC_UR04 | check functionality of"Iconnect" | TEST url | Desktop | 1)Enter URL 2)Enter valid user id and password 3)Move curser on "iconnect" option 4)click on "isocial events" | 1)Color of "iconnect"should be red 2)dropdown option list open 3)user should be redirected to "isocial event"page 4)create new event button should be displayed | 1)Color of "iconnect"is red 2)dropdown option list is open 3)user is redirecting to "isocial event"page 4)create new event button is displaying 5)Events should be displayed | pass
| TC_UR05 | Check functionality of view event | TEST url | Desktop | 1)Enter URL 2)Enter valid user id and password 3)Move curser on "iconnect" option 4)click on "isocial events" 5)click on event | event should be open | event is open | fail | 1)User can edit event data